CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

– Hanoi, Aug 2026 –

Table of Contents

Change Log	3

I. Project Overview	4

1. Scope and Purpose	4

2. Assumptions & Constraints	4

3. Cost & Time Estimations	5

4. Capacity Planning	11

5. Project Objectives	11

6. Risks and Mitigations	12

II. Management Approach	13

1. Project Process/Methodology	13

2. Quality Management	13

3. Project Training Plan	13

4. Responsibility Assignments	14

5. Project Communications	16

6. Configuration Management	18

6.1 Document Management	18

6.2 Source Code Management	18

6.3 Tools & Infrastructures	18

Definition and Acronyms	19

# Change Log

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| v1.0 |  |  |  |
| 28/09/2026 | A | TrangCTH | Added Project Overview sections |
| 29/09/2026 | A | TrangCTH | Added Management Approach sections |
| 30/09/2026 | A | TrangCTH | Added Configuration Management and finalized Report 2 |
| 1/10/2026 | M | CaoNM | Modified Scope and Purpose |
| 1/10/2026 | M | CaoNM | Modified Assumptions & Constraints |
| 1/10/2026 | M | CaoNM | Modified Cost & Time Estimations |
| 2/10/2026 | M | CaoNM | Modified Project Objectives |
| 2/10/2026 | M | CaoNM | Modified Capacity Planning |
| 2/10/2026 | M | CaoNM | Modified Project Objectives |
| 2/10/2026 | M | CaoNM | Modified Risks and Mitigations |
| 2/10/2026 | M | CaoNM | Modified Project Process/Methodology |
| 2/10/2026 | M | CaoNM | Modified Project Training Plan |
| 3/10/2026 | A | CaoNM | Added Definition and Acronyms |
| v2.0 |  |  |  |
| 17/10/2026 | M | TrangCTH | Modified Cost & Time Estimations |

*A - Added M - Modified D - Deleted

# I. Project Overview

## 1. Scope and Purpose

The GenZ Cinema & Music Box Management System (GCMB) project aims to develop a centralized, web-based platform to replace the fragmented use of KiotViet, spreadsheets, and other manual processes across the GenZ Cinema & Music Box chain. The system focuses on standardizing and integrating key operational and financial activities, reducing manual reconciliation, improving data consistency and accountability, and providing centralized visibility across branches. The system provides role-based access for four primary internal business roles: Head Office Manager, Branch Manager, Receptionist, and Accountant. Customers interact with a limited customer-facing function to place F&B orders through an in-room QR interface.

In scope, GCMB covers five major feature areas: System Configuration Management, Service Management, Resource Management, Workforce Management and Business Performance Management. These features support activities such as room booking and status management, check-in/check-out, billing and payments, deposits and refunds, staff-assisted and customer QR-based F&B ordering, inventory, equipment maintenance , shift scheduling, attendance, payroll, expenses, cash reconciliation, and multi-branch reporting. External services such as SePay, cloud storage, and email may be integrated where required.

Out of scope for the current release are a customer-facing booking portal, hardware barcode-scanner integration, official tax report generation, content licensing and copyright compliance management, regulatory and safety compliance enforcement, and recipe/BOM-based ingredient management. These exclusions define the project boundary and help prevent uncontrolled scope expansion.

GCMB is related to the existing KiotViet and spreadsheet-based workflows currently used by GenZ Cinema. Rather than maintaining separate operational records across these tools, GCMB is intended to consolidate the essential workflows into a unified management platform and reduce duplicate data entry and manual cross-checking.

## 2. Assumptions & Constraints

| No | Description | Note |
| --- | --- | --- |
| Assumptions |  |  |  |
| 1 | GenZ Cinema & Music Box representatives will maintain regular communication with the project team to clarify business requirements and operational workflows when necessary. | Stakeholder |
| 2 | Stakeholders will provide feedback at agreed project milestones so that requirements, designs, and implemented features can be reviewed and refined in a timely manner. | Schedule |
| 3 | Company representatives and relevant end users will be available to participate in User Acceptance Testing (UAT) and provide acceptance feedback on the delivered system. | Quality |
| 4 | Business rules, operational information, and sample data provided by GenZ Cinema & Music Box are assumed to be sufficiently accurate and up to date for development and testing. | Data |
| 5 | Required third-party services, such as SePay, cloud storage, and email services, are assumed to remain available and provide suitable interfaces for integration during development and testing. | External Interfaces |
| Constraints |  |  |  |
| 1 | The project must be completed within the university-defined Capstone Project schedule, including development, testing, stakeholder review, and final delivery. | Schedule |
| 2 | The project is developed by a student team with limited development time, personnel, infrastructure, and access to the company's production environment. | Resources |
| 3 | Development is limited to the agreed GCMB scope. Features explicitly identified as out of scope will not be implemented in the current release. | Scope |
| 4 | GCMB will be developed as a web-based application and must support the four defined internal business roles: Head Office Manager, Branch Manager, Receptionist, and Accountant. A limited Customer interaction is also supported for in-room QR-based F&B ordering. | Technology |
| 5 | Integration with external services is subject to the availability, API capabilities, access permissions, and technical limitations of those services. | External Interfaces |
| 6 | Existing operational data is distributed across KiotViet, spreadsheets, and manual records; therefore, the project is constrained by the accessibility and consistency of data provided by the company. | Existing Software / Data |

## 3. Cost & Time Estimations

The project is planned to be completed within 14 weeks by a team of 5 members. Each member is expected to contribute approximately 5 person-days (pds) per week, resulting in a total estimated project effort of 350 pds.

The detailed work packages, estimated efforts, and due dates are presented in the following table. Due dates for project reports and documents shall follow the corresponding dates defined in the Project Tracking sections to ensure consistency across project documents.

| # | Work Package | Effort (pds) | Due Date |
| --- | --- | --- | --- |
| 1 | Stage 1: Project Initiation (Weeks 1–2) | 30 | 8/10/2026 |
| 1.1 | Report 1: Project Introduction | 10 | 8/10/2026 |
| 1.2 | Requirement Elicitation: stakeholder interviews/surveys, current-process analysis and requirement consolidation | 20 | 8/10/2026 |
| 2. | Stage 2: Project Planning & Initial Requirements (weeks 3 - 4) | 70 | 9/10/2026 |
| 2.1 | Report 2: Project Management Plan | 15 | 4/10/2026 |
| 2.2 | Report 3: Software Requirements Specification (SRS) | 30 | 8/10/2026 |
| 2.3 | UI/UX Design and Prototypes | 25 | 9/10/2026 |
| 3 | Stage 3: Iterative Development (Weeks 5–10) | 150 | 13/11/2026 |
| 3.1 | Iteration 1: System Configuration Management + Service Management (42 UCs) + SDS + Testing + User Guide + Software Release (10/10–21/10/2026; Weeks 5–7 ) | 50 | 21/10/2026 |
| 3.1.1 | UC-01 Change Password | 0.5 | 10/10/2026 |
| 3.1.2 | UC-02 Reset Password | 1.5 | 10/10/2026 |
| 3.1.3 | UC-03 Update Account Information | 0.5 | 10/10/2026 |
| 3.1.4 | UC-04 Create User Account | 1.5 | 10/10/2026 |
| 3.1.5 | UC-05 View User Accounts | 0.5 | 10/10/2026 |
| 3.1.6 | UC-06 Set Account Role | 2.0 | 12/10/2026 |
| 3.1.7 | UC-07 Deactivate User Account | 0.5 | 12/10/2026 |
| 3.1.8 | UC-08 View Audit Log | 1.0 | 12/10/2026 |
| 3.1.9 | UC-09 Create Branch | 0.5 | 12/10/2026 |
| 3.1.10 | UC-10 View Branch List | 0.5 | 12/10/2026 |
| 3.1.11 | UC-11 Update Branch | 0.5 | 12/10/2026 |
| 3.1.12 | UC-12 Set Branch Manager | 1.0 | 13/10/2026 |
| 3.1.13 | UC-13 Change Branch Operating Status | 0.5 | 13/10/2026 |
| 3.1.14 | UC-14 Create Room Type | 0.5 | 13/10/2026 |
| 3.1.15 | UC-15 View Room Types | 0.5 | 13/10/2026 |
| 3.1.16 | UC-16 Update Room Type | 0.5 | 13/10/2026 |
| 3.1.17 | UC-17 Change Room Type Status | 0.5 | 13/10/2026 |
| 3.1.18 | UC-18 Delete Room Type | 0.5 | 13/10/2026 |
| 3.1.19 | UC-19 Create Room Price | 2.0 | 14/10/2026 |
| 3.1.20 | UC-20 View Room Prices | 0.5 | 14/10/2026 |
| 3.1.21 | UC-21 Update Room Price | 1.5 | 14/10/2026 |
| 3.1.22 | UC-22 Change Room Price Status | 0.5 | 14/10/2026 |
| 3.1.23 | UC-23 Create Combo Package | 1.5 | 14/10/2026 |
| 3.1.24 | UC-24 View Combo Packages | 0.5 | 14/10/2026 |
| 3.1.25 | UC-25 Update Combo Package | 0.5 | 15/10/2026 |
| 3.1.26 | UC-26 Deactivate Combo Package | 0.5 | 15/10/2026 |
| 3.1.27 | UC-27 Change Combo Package Status | 0.5 | 15/10/2026 |
| 3.1.28 | UC-28 Create Room | 0.5 | 15/10/2026 |
| 3.1.29 | UC-29 Update Room | 0.5 | 15/10/2026 |
| 3.1.31 | UC-31 Delete Room | 1.0 | 15/10/2026 |
| 3.1.32 | UC-32 View Rooms | 1.0 | 15/10/2026 |
| 3.1.33 | UC-33 Set Room Operating Status | 0.5 | 15/10/2026 |
| 3.1.34 | UC-34 Create Booking | 3.0 | 16/10/2026 |
| 3.1.35 | UC-35 View Bookings | 1.0 | 16/10/2026 |
| 3.1.36 | UC-36 Update Booking | 2.5 | 17/10/2026 |
| 3.1.37 | UC-42 Collect Booking Deposit | 3.0 | 17/10/2026 |
| 3.1.38 | UC-37 Cancel Booking | 3.0 | 19/10/2026 |
| 3.1.40 | UC-44 Refund Booking Deposit | 2.0 | 19/10/2026 |
| 3.1.41 | UC-38 Check In Guest | 2.0 | 20/10/2026 |
| 3.1.42 | UC-39 Change Room | 2.5 | 20/10/2026 |
| 3.1.43 | UC-40 Extend Room Stay | 2.0 | 21/10/2026 |
| 3.1.44 | UC-41 Check Out Guest | 4.0 | 21/10/2026 |
| 3.2 | Iteration 2: Service Management + Resource Management + Workforce Management (48 UCs) + SDS + Testing + User Guide + Software Release (22/10–02/11/2026; Weeks 7–9) | 50 | 02/11/2026 |
| 3.2.1 | UC-54 Create Inventory Item | 0.5 | 22/10/2026 |
| 3.2.2 | UC-55 View Inventory | 0.5 | 22/10/2026 |
| 3.2.3 | UC-56 Update Inventory Item | 0.5 | 22/10/2026 |
| 3.2.4 | UC-57 Delete Inventory Item | 0.5 | 22/10/2026 |
| 3.2.5 | UC-58 Record Stock Receipt | 2.0 | 22/10/2026 |
| 3.2.6 | UC-59 Adjust Stock Quantity | 2.0 | 23/10/2026 |
| 3.2.7 | UC-45 Create Menu Item | 0.5 | 23/10/2026 |
| 3.2.8 | UC-46 View Menu Items | 0.5 | 23/10/2026 |
| 3.2.9 | UC-47 Update Menu Item | 0.5 | 23/10/2026 |
| 3.2.10 | UC-48 Deactivate Menu Item | 0.5 | 23/10/2026 |
| 3.2.11 | UC-49 Delete Menu Item | 0.5 | 23/10/2026 |
| 3.2.12 | UC-50 Add Items to Booking | 2.5 | 24/10/2026 |
| 3.2.13 | UC-51 Submit Item Request | 3.0 | 24/10/2026 |
| 3.2.14 | UC-52 View Booking Items | 0.5 | 24/10/2026 |
| 3.2.15 | UC-53 Confirm Item Request | 2.0 | 26/10/2026 |
| 3.2.16 | UC-60 Create Equipment Category | 0.5 | 26/10/2026 |
| 3.2.17 | UC-61 View Equipment Categories | 0.5 | 26/10/2026 |
| 3.2.18 | UC-62 Update Equipment Category | 0.5 | 26/10/2026 |
| 3.2.19 | UC-63 Deactivate Equipment Category | 0.5 | 26/10/2026 |
| 3.2.20 | UC-64 Delete Equipment Category | 0.5 | 26/10/2026 |
| 3.2.21 | UC-65 Create Equipment Asset | 1.5 | 27/10/2026 |
| 3.2.22 | UC-66 View Equipment Assets | 0.5 | 27/10/2026 |
| 3.2.23 | UC-67 Update Equipment Asset | 1.0 | 27/10/2026 |
| 3.2.24 | UC-68 Deactivate Equipment Asset | 0.5 | 27/10/2026 |
| 3.2.25 | UC-69 Delete Equipment Asset | 0.5 | 27/10/2026 |
| 3.2.26 | UC-70 Create Equipment Incident Report | 2.0 | 27/10/2026 |
| 3.2.27 | UC-72 View Equipment Incidents | 0.5 | 28/10/2026 |
| 3.2.28 | UC-73 Assess Equipment Incident | 1.5 | 28/10/2026 |
| 3.2.29 | UC-71 Record Repair Outcome | 2.5 | 28/10/2026 |
| 3.2.30 | UC-74 Create Equipment Transfer Request | 1.5 | 29/10/2026 |
| 3.2.31 | UC-75 Confirm Equipment Handover | 1.5 | 29/10/2026 |
| 3.2.32 | UC-76 Confirm Equipment Receipt | 1.5 | 29/10/2026 |
| 3.2.33 | UC-77 Create Staff Record | 1.5 | 30/10/2026 |
| 3.2.34 | UC-78 View Staff Records | 0.5 | 30/10/2026 |
| 3.2.35 | UC-79 Update Staff Record | 1.0 | 30/10/2026 |
| 3.2.36 | UC-80 Deactivate Staff Record | 0.5 | 30/10/2026 |
| 3.2.37 | UC-81 Set Employee Branch | 1.0 | 30/10/2026 |
| 3.2.38 | UC-82 Transfer Employee | 1.5 | 31/10/2026 |
| 3.2.39 | UC-85 Set Weekly Shift Availability | 1.5 | 31/10/2026 |
| 3.2.40 | UC-84 View Shift Schedule | 0.5 | 31/10/2026 |
| 3.2.41 | UC-83 Register for Shift | 1.5 | 31/10/2026 |
| 3.2.42 | UC-86 Update Shift Schedule | 1.5 | 02/11/2026 |
| 3.2.43 | UC-87 Record Daily Attendance | 2.0 | 02/11/2026 |
| 3.2.44 | UC-88 View Attendance Records | 0.5 | 02/11/2026 |
| 3.2.45 | UC-89 Close Monthly Attendance Sheet | 1.0 | 02/11/2026 |
| 3.2.46 | UC-90 View Personal Work Records | 0.5 | 02/11/2026 |
| 3.2.47 | UC-126 Update Order Service Status | 0.5 | 02/11/2026 |
| 3.2.48 | UC-127 Update Tax Invoice Request Status | 0.5 | 02/11/2026 |
| 3.3 | Iteration 3: Workforce Management + Business Performance Management (35 UCs) + SDS + Testing + User Guide + Software Release (03/11–13/11/2026; Weeks 9–10 ) | 50 | 13/11/2026 |
| 3.3.1 | UC-102 Record Incoming Fund | 1.0 | 3/11/2026 |
| 3.3.2 | UC-103 Allocate Branch Fund | 1.5 | 3/11/2026 |
| 3.3.3 | UC-104 View Accountant Fund | 0.5 | 3/11/2026 |
| 3.3.4 | UC-115 Create Expense Category | 0.5 | 3/11/2026 |
| 3.3.5 | UC-116 View Expense Categories | 0.5 | 3/11/2026 |
| 3.3.6 | UC-117 Update Expense Category | 0.5 | 3/11/2026 |
| 3.3.7 | UC-118 Deactivate Expense Category | 0.5 | 3/11/2026 |
| 3.3.8 | UC-119 Delete Expense Category | 0.5 | 4/11/2026 |
| 3.3.9 | UC-107 Create Payment Request | 1.5 | 4/11/2026 |
| 3.3.10 | UC-109 View Payment Requests | 0.5 | 4/11/2026 |
| 3.3.11 | UC-110 Review Payment Request | 1.5 | 4/11/2026 |
| 3.3.12 | UC-108 Pay Approved Request | 2.0 | 5/11/2026 |
| 3.3.13 | UC-111 Create Reimbursement Request | 2.0 | 5/11/2026 |
| 3.3.14 | UC-113 View Reimbursement Requests | 0.5 | 5/11/2026 |
| 3.3.15 | UC-114 Review Reimbursement Request | 1.5 | 5/11/2026 |
| 3.3.16 | UC-112 Pay Reimbursement | 2.0 | 6/11/2026 |
| 3.3.17 | UC-120 View Expense History | 1.0 | 6/11/2026 |
| 3.3.18 | UC-91 Calculate Monthly Payroll | 3.0 | 7/11/2026 |
| 3.3.19 | UC-92 View Monthly Payroll | 0.5 | 7/11/2026 |
| 3.3.20 | UC-93 Export Monthly Payroll | 1.0 | 7/11/2026 |
| 3.3.21 | UC-94 Update Monthly Payroll | 1.5 | 7/11/2026 |
| 3.3.22 | UC-95 Confirm Monthly Payroll | 1.0 | 7/11/2026 |
| 3.3.23 | UC-96 Pay Salary Advance | 1.5 | 9/11/2026 |
| 3.3.24 | UC-97 Pay Monthly Salary | 2.5 | 9/11/2026 |
| 3.3.25 | UC-98 Record Daily Cash Closing | 2.5 | 10/11/2026 |
| 3.3.26 | UC-99 View Daily Cash Closings | 0.5 | 10/11/2026 |
| 3.3.27 | UC-100 View Cash Variance Alerts | 1.0 | 10/11/2026 |
| 3.3.28 | UC-101 Confirm Daily Cash Reconciliation | 2.0 | 10/11/2026 |
| 3.3.29 | UC-106 Adjust Financial Transaction | 1.5 | 11/11/2026 |
| 3.3.30 | UC-105 Close Financial Period | 2.0 | 11/11/2026 |
| 3.3.31 | UC-121 View Chain Dashboard | 3.0 | 12/11/2026 |
| 3.3.32 | UC-122 View Branch Dashboard | 2.0 | 12/11/2026 |
| 3.3.33 | UC-123 View Monthly Performance Report | 3.0 | 13/11/2016 |
| 3.3.34 | UC-124 View Expense Breakdown Report | 1.5 | 13/11/2016 |
| 3.3.35 | UC-125 Export Tax Accounting Data | 2.0 | 13/11/2016 |
| 4 | Stage 4: Verification, Deployment & Project Closure (Weeks 11–14) | 100 | 11/12/2026 |
| 4.1 | Complete System and Integration Testing, defect fixing and regression testing | 30 | 23/11/2026 |
| 4.2 | System Deployment and Deployment Verification | 15 | 26/11/2026 |
| 4.3 | User Acceptance Testing (UAT) and stakeholder feedback handling | 15 | 1/12/2026 |
| 4.4 | Demo Data Preparation and Final System Demonstration | 10 | 3/12/2026 |
| 4.5 | Finalization of Reports 1–7 and supporting project documentation | 25 | 10/12/2026 |
| 4.6 | Final Software Package and Project Handover | 5 | 11/12/2026 |
|  | TOTAL PROJECT EFFORT | 350 | 11/12/2026 |

## 4. Capacity Planning

| Item | Value |
| --- | --- |
| Hours per person per week | 30 h (6 h/day × 5 days) |
| Team total per week | 150 h/week (5 people × 30 h) |
| Total duration | 14 weeks |
| Gross capacity | 2,100 h (150 h/week × 14 weeks) |
| Buffer (meetings, reviews, unplanned, weekends) | 168 h (2,100 × 8%) |
| Effective working capacity | 1,932 h (2,100 × 92%) |

## 5. Project Objectives

| # | Metric | Unit | Planned | Actual | Notes / References |
| --- | --- | --- | --- | --- | --- |
| 1 | Effort Usage | Person-day | ≥ 350 pds | TBD | Based on Cost & Time Estimation |
| 2 | Review Defects | No of defects | ≥ 50 | TBD | Defects identified through requirement, design, code, and document reviews |
| 3 | Unit Test Defects | No of defects | ≥ 40 | TBD | Defects detected during Unit Testing |
| 4 | Integration Test Defects | No of defects | ≥ 30 | TBD | Defects detected during Integration Testing |
| 5 | System Test Defects | No of defects | ≥ 20 | TBD | Defects detected during System Testing |
| 6 | Acceptance Test Defects | No of defects | ≥ 10 | TBD | Defects detected during Acceptance Testing |
| 7 | Timeliness | % | ≥ 90% | TBD | On-time deliverables / Total project deliverables × 100% |
| 8 | Requirement Completeness | % | > 75% | TBD | Implemented and accepted requirements / Total baseline requirements × 100% |
| 9 | Test Case Execution Rate | % | ≥ 95% | TBD | Executed test cases / Planned test cases × 100% |
| 10 | Critical Defects at Release | No of defects | 0 | TBD | No unresolved Critical defects before final release |

## 6. Risks and Mitigations

| # | Risk | Prob | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R01 | Requirements may change significantly after the requirements baseline due to new or clarified business needs from GenZ Cinema & Music Box. | Medium | High | Confirm and baseline requirements with stakeholders at the end of Stage 1. Any subsequent change request must undergo impact analysis on scope, effort, and schedule before acceptance. Major changes will be deferred to a later release if they cannot be accommodated within the project schedule. |
| R02 | Stakeholder feedback or approval may be delayed, affecting requirement confirmation, iteration reviews, or UAT activities. | Medium | High | Maintain regular communication with company representatives and arrange review/UAT sessions in advance. Submit deliverables early enough for stakeholder review and follow up on pending feedback. If feedback is delayed, continue with previously approved requirements and update affected work after confirmation. |
| R03 | A team member may become temporarily unavailable or contribute less than planned due to academic workload, health, or personal commitments. | Medium | High | Maintain shared project documentation and source code so work can be transferred between members. Monitor workload weekly and redistribute tasks when a member becomes unavailable. Weekend buffer capacity may be used when necessary to recover schedule delays. |
| R04 | Development activities or deliverables may fall behind the planned 14-week schedule, especially during the three development iterations. | Medium | Medium | Track progress against the WBS and Project Tracking plan weekly. Prioritize critical work packages and agreed in-scope features. Reallocate team capacity and use the Saturday/Sunday schedule buffer when necessary to recover delays. |
| R05 | Required external services or company resources, such as SePay integration information, cloud services, email services, sample data, or access credentials, may not be available when needed. | Medium | Medium | Identify external dependencies early and request required access, documentation, and sample data in advance. Where possible, use test/sandbox environments or controlled test data so development can continue while waiting for external resources. |

# II. Management Approach

## 1. Project Process/Methodology

The project follows a hybrid approach that combines the Waterfall model for the early project phases and an Iterative & Incremental (I&I) model for the development phase. The overall process is divided into three stages as shown below.

## 2. Quality Management

The team will apply early testing throughout the project to find and fix defects as soon as possible. Requirements, designs, code, and test cases will be reviewed regularly to prevent defects from moving to later stages.During development, developers will perform Unit Testing before integrating features. Integration Testing and System Testing will be carried out after implementation, while Acceptance Testing will be performed with the customer before the final release. Defects found at each stage will be recorded, fixed, and retested.The team aims to find more defects in earlier stages, following the target:

Review Defects > UT Defects > IT Defects > ST Defects > AT Defects.

The quality results will be tracked based on the objectives defined in Project Objectives.

## 3. Project Training Plan

| Training Area | Participants | When, Duration |
| --- | --- | --- |
| Java Spring Boot | Developers | Week 1–2, 2 sessions |
| ReactJS | Developers | Week 1–2, 2 sessions |
| PostgreSQL | Developers | Week 2, 1 session |
| Git & GitHub | All team members | Week 1, 1 session |
| Requirements & Use Case | All team members | Week 1–2, 1 session |
| Software Testing & Defect Management | Tester, Developers | Week 2, 1 session |
| Project Documentation | All team members | Week 1, 1 session |

## 4. Responsibility Assignments

Project Manager / Tester – Nguyễn Minh Cao: responsible for overall project coordination, schedule and progress control, risk and quality management, work allocation, test planning and execution, deliverable review, and final project readiness.

Business Analyst – Cù Thị Huyền Trang: responsible for business investigation, requirement elicitation and analysis, AS-IS/TO-BE processes, business rules, use cases, SRS preparation, requirement clarification, traceability, acceptance scenarios, and user documentation.

Fullstack Developers – Đào Văn Huy, Nguyễn Tuấn Thành, Nguyễn Văn Trọng: responsible for technical design, database/API/UI implementation, unit testing, integration support, defect fixing, technical documentation, deployment preparation, and delivery of software packages.

Supervisor – Nguyễn Thị Hạnh: provides academic supervision, reviews major project deliverables and project progress, and gives guidance at project milestones. The Supervisor is not included as a project execution role in the RACI table.

RACI Chart: R~Responsible, A~Accountable, C~Consulted, I~Informed

| Work Package | HuyDVHE180086 | TrangCTHHE194251 | ThanhNTHE181132 | TrongNVHE181249 | CaoNMHE181251 |
| --- | --- | --- | --- | --- | --- |
| Project Initiation & Report 1 – Project Introduction | C | R | C | C | A |
| Project Planning & Report 2 – Project Management Plan | C | C | C | C | A/R |
| Requirement Elicitation & Business Process Analysis | C | R | C | C | A |
| Report 3 – SRS v0.9 / Overall Requirements | C | R | C | C | A |
| Vertical Prototype / Proof of Concept | R | C | R | R | A |
| Report 4 – High-Level SDS v1.0 | R | C | R | R | A |
| Test Planning / Report 5 Test Documentation | C | C | C | C | A/R |
| Detailed Requirements for each Iteration | C | R | C | C | A |
| Detailed SDS for Iterations 1–3 | R | C | R | R | A |
| Software Implementation – Iterations 1–3 | R | C | R | R | A |
| Unit Testing | R | I | R | R | A |
| Integration Testing | R | C | R | R | A/R |
| System Testing – FRs & NFRs | C | C | C | C | A/R |
| Acceptance Test Preparation & Support | C | R | C | C | A/R |
| Defect Fixing & Regression Testing | R | C | R | R | A/R |
| Software Package v1, v2, v3 & Final Package | R | I | R | R | A |
| Report 6 – User Guides | C | R | C | C | A |
| Report 7 – Final Project Report | C | R | C | C | A |
| Final Presentation & Defense Preparation | R | R | R | R | A/R |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Daily Team Meeting | PM, BA, Developers | Share daily progress, blockers, current tasks and coordination needs | Daily during active development, 15–30 minutes | Online/offline meeting; Zalo/Google Meet |
| Weekly Project Meeting | All team members | Review weekly progress, completed work, schedule, risks, issues and next-week plan | Once per week | Offline/online meeting; meeting minutes recorded and shared |
| Supervisor Review Meeting | Supervisor and project team | Report progress, review major deliverables, receive academic guidance and resolve project-level issues | Weekly or according to supervisor schedule | Offline meeting / Google Meet; project documents used for review |
| Requirement Elicitation / Clarification Meeting | BA, PM and relevant GenZ business stakeholders | Collect, validate and clarify business requirements and business rules | During Weeks 1–5 and later when clarification is required | Interview / offline meeting / call; notes, audio/video evidence where required |
| Requirement & SRS Review | BA, PM, Developers | Validate feasibility, consistency, completeness and shared understanding of requirements before implementation | Before baselining each SRS version / iteration | Document review; Google Drive/Docs and team discussion |
| Technical Design Review | PM, Developers, BA when business clarification is needed | Review architecture, database, APIs, interfaces and detailed design before implementation | At design stage and at the beginning of each iteration | Team review; SDS, diagrams, GitHub |
| Iteration Planning Meeting | PM, BA, Developers | Select requirements and features for the next iteration and confirm workload | Beginning of each implementation iteration | Team meeting; Project Tracking/WBS |
| Iteration Review / Demo | All team members; relevant stakeholders when available | Demonstrate completed functions, collect feedback and identify required corrections | End of each iteration | Software demo and review meeting |
| Testing & Defect Review | PM/Tester and Developers; BA for requirement-related defects | Review test results, classify defects, assign fixes and confirm retesting | During testing; more frequently near iteration/release deadlines | Test reports, issue list, GitHub/project tracking |
| Git / Source Code Communication | Developers and PM | Coordinate branches, pull requests, merges, code reviews and technical changes | Continuously during implementation | Git and GitHub |
| Document Collaboration | All team members | Maintain and review Report 1–7, requirements, design, test documents and project evidence | Throughout the project | Google Drive / Google Docs / shared project folder |
| Urgent Issue Communication | All relevant members | Resolve blocking issues, requirement questions, schedule risks or urgent defects | As needed | Zalo group / direct call |
| Final Review & Defense Preparation | Entire team | Finalize documents/software, prepare sample data, presentation and defense rehearsal | Weeks 13–14 | Offline team meeting, presentation rehearsal and final checklist |

## 6. Configuration Management

### 6.1 Document Management

All project documents are stored and managed in a shared Google Drive repository with a predefined folder structure for each deliverable, including Report 1–7, requirements, design, testing documents, meeting minutes, and supporting evidence. Each document shall follow a consistent naming and versioning convention. Major versions are created when a document is baselined or formally submitted, while minor versions are used for reviewed updates during an iteration. Changes to important documents such as SRS, SDS, Project Management Plan, and Test Documentation must be reviewed by the responsible member and approved by the Project Manager before being treated as the current baseline. Google Drive version history is used to trace document changes, while obsolete versions are retained for reference rather than overwritten or deleted.

### 6.2 Source Code Management

Project source code is managed using GitHub. The team maintains a shared repository containing the frontend, backend, database scripts, and configuration files. Development work is performed on separate branches and merged into the main integration branch through pull requests after review and testing. Developers are responsible for committing changes frequently with meaningful commit messages and synchronizing with the remote repository before starting new work. Stable versions produced at the end of each implementation iteration are tagged or released as Version 1, Version 2, and Version 3, while the final validated build is tagged as the final release. Sensitive information such as passwords, API keys, database credentials, and service secrets must not be committed to the repository and should be stored in environment variables or deployment configuration.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | ReactJS (Frontend), Java / Spring Boot (Backend), REST API |
| Database | PostgreSQL |
| Architecture | Web Client–Server architecture with centralized backend API and database |
| IDEs / Editors | Visual Studio Code, IntelliJ IDEA |
| Diagramming | Visual Paradigm, Draw.io |
| Documentation | Microsoft Office, Google Docs / Sheets / Slides |
| Version Control | Git & GitHub (Source Code), Google Drive (Documents) |
| External Services | SePay Payment Service, Cloud Storage Service, Email Service |
| Deployment Server | Cloud / VPS with Docker-based deployment |
| Client Environment | Web Browser |
| Testing | JUnit, API testing tool such as Postman, project test documents in Report 5 |
| Project Management | Project Tracking Excel Template, Weekly Report Template, GitHub Issues/Tasks where applicable |
| Communication | Zalo, Google Meet, Offline Meetings |

# Definition and Acronyms

| Acronym | Definition |
| --- | --- |
| GCMB | GenZ Cinema & Music Box Management System |
| TBD | To Be Determined |
| SRS | Software Requirements Specification |
| SDS | Software Design Specification |
| BA | Business Analyst |
| PM | Project Manager |
| UT Defects | Unit Testing Defects |
| IT Defects | Integration Testing Defects |
| ST Defects | System Testing Defects |
| AT Defects | Acceptance Testing Defects |
| R | Risk ID – Identifier used for project risk |
| pds | Person-days |
| UC-AUTH | Use Case – Authentication and Authorization |
| UC-BRN | Use Case – Branch Management |
| UC-ROOM | Use Case – Room and Pricing Management |
| UC-BKG | Use Case – Booking and Room Operations |
| UC-DEP | Use Case – Deposit Management |
| UC-ORD | Use Case – Service and F&B Order Management |
| UC-INV | Use Case – Inventory Management |
| UC-EQP | Use Case – Equipment Management |
| UC-STF | Use Case – Staff Management |
| UC-SHF | Use Case – Shift Scheduling and Attendance Management |
| UC-PAY | Use Case – Payroll Management |
| UC-CSH | Use Case – Cashflow and Financial Reconciliation |
| UC-EXP | Use Case – Expense and Reimbursement Management |
| UC-RPT | Use Case – Reporting and Dashboard |
| Medium | A moderate level of risk probability or impact that requires monitoring and appropriate mitigation actions. |
| High | A significant level of risk probability or impact that requires priority attention and strong mitigation actions. |